# engineering review - w20 notes

date: may 14 | attendees: K.M., S.F., A.S., T.R. + ext.

--- rough notes, not cleaned up ---

STATUS project X:

km: phase 1 done, dv testing passed. phase 2 starts next week. on track for SOP Q4/27

sf: BOM finalized, procurement placed orders last week. lead times ok except supplier X -> 14 weeks, critical path

QUALITY ISSUE plant B:

as: defect rate 1.8% vs 0.5% target!! crimp tolerance drift. 8D opened. CA deadline 22 may

action: as sends rca to km by fri. corrective action plan by monday. if not resolved -> escalate to ops director

financial impact discussed: ~€58k if rate stays through W21. need to fix.

CUSTOMER REVIEW prep:

june 3 at customer site. tr to prepare agenda. 3 of 7 open items from last review still open!

critical: PPAP docs needed by may 30 (as owns). customer will ask about timeline. DO NOT commit to earlier than Q4/27

km: also check on 2 open NCRs from last audit - need closure evidence

SUPPLIER ISSUES:

supplier X: 14-week lead time, critical parts. airfreight approved for initial batch.

supplier Y: quality audit scheduled june 10. tr to coordinate.

NEXT STEPS (action items):

1. as - 8D rca report - fri may 16

2. as - PPAP docs complete - may 30

3. tr - june 3 agenda - may 28

4. km - supplier X airfreight confirm - may 15

5. sf - BOM review for phase 2 - may 21

6. tr - NCR closure evidence - may 24