# Weekly Team Status Report — KW20 / May 2026

Team: Digital Solutions · Prepared: May 20, 2026 · Owner: Demo User

# This Week — Completed

Copilot pilot evaluation completed for Contoso Manufacturing — positive results, proposal ready

Teams Premium deployment for Fabrikam Logistics — 40 users onboarded successfully

Quarterly Business Review deck for Northwind Traders — delivered and approved

Technical architecture review: Azure OpenAI integration for Alpine Ski House

Partner certification renewed: Microsoft AI Cloud Partner Program

# In Progress

Contoso M365 Copilot full deployment proposal — due June 2 (needs ROI model)

Fabrikam Logistics: SharePoint migration — 60% complete, on track for June 30

Northwind Traders: Security assessment — waiting for customer IT team input

Adventure Works: Teams Rooms deployment — pilot running, 3 rooms online

# Blockers / Risks

Contoso ROI case: Need internal benchmark data from product team — requested May 15, still pending

Fabrikam migration: Customer SharePoint admin on vacation until June 1 — potential delay

Budget freeze at Northwind Traders until Q3 — opportunity at risk

# Next Week Priorities

Finish Contoso ROI case — present at June 2 call

Fabrikam: Resume SharePoint migration — coordinate with returning admin

Pipeline review prep for Thursday team meeting

Enroll in new Microsoft AI certification track (deadline June 15)